## Project info
Project name | Online Book Store
Group name | Coder Heads
student name |  | ID
1. Shadman S. Khan |  | 1611918042
2. MD.Shaheduzzaman Shahed 1610985042 |  | 1610985042
3. MD.Minhazul Islam | … | 1620695042
4. Salsavil Kayyum | … | 1620307042

## WBS
sl | task name | description | deadline | responsible name | owner | comment
1 | Project planning | Planning with pen and paper | 2019-02-06 | Shadman S. Khan,MD. Shaheduzzaman Shahed,MD. Minhazul Islam,Salsavil Kayyum | Shadman S. Khan
2 | Back-end design | design in pen and paper | 2019-02-06 | Shadman S. Khan,MD. Shaheduzzaman Shahed,MD. Minhazul Islam,Salsavil Kayyum | MD. Shaheduzzaman Shahed
3 | Front-end sletch | sketch in pen and paper | 2019-02-11 | Shadman S. Khan | MD. Minhazul Islam
4 | design db structure | design tables of db in pen and paper | 2019-02-12 | MD. Shaheduzzaman Shahed | Salsavil Kayyum
5 | develop db structure | develop db structure on mysql db | 2019-02-13 | Shadman S. Khan,MD. Shaheduzzaman Shahed,MD. Minhazul Islam,Salsavil Kayyum | Salsavil Kayyum
6 | develop login and registration | developing login and registration page roughly | 2019-02-26 | MD. Minhazul Islam | MD. Minhazul Islam
7 | develop homepage | developing homepage roughly | 2019-02-25 | MD. Shaheduzzaman Shahed | MD. Shaheduzzaman Shahed
8 | develop book-detail page | developing book description page | 2019-02-27 | Salsavil Kayyum | Salsavil Kayyum
9 | develop pop-ups | developing pop-ups for a page | 2019-03-02 | Shadman S. Khan | Shadman S. Khan
10 | Sorting and filtering | Sorting and filter coding PHP + HTML | 2019-03-16 | Shadman S. Khan, MD. Minhazul Islam | MD. Minhazul Islam
11 | User access controls | user access controls using PHP | 2019-04-02 | Salsavil Kayyum, MD. Shaheduzzaman Shahed | MD. Shaheduzzaman Shahed
12 | Data entry | Data entry of books and others | 2019-03-19 | Salsavil Kayyum, MD. Shaheduzzaman Shahed | MD. Shaheduzzaman Shahed
13 | creating animations | creating animations for pages | 2019-03-24 | Shadman S. Khan, MD. Minhazul Islam | MD. Minhazul Islam
14 | creating auto timings | creating auto timings for | 2019-03-30 | Shadman S. Khan, MD. Minhazul Islam | Shadman S. Khan
15 | Login Testing | Testing and bug fixing | 2019-04-15 | MD. Minhazul Islam | MD. Minhazul Islam
16 | Browse Testing | Testing and bug fixing | 2019-04-17 | Shadman S. Khan | Shadman S. Khan
17 | Transaction Testing | Testing and bug fixing | 2019-04-17 | Salsavil Kayyum | Salsavil Kayyum
18 | Database Testing | Testing and bug fixing | 2019-04-20 | MD. Shaheduzzaman Shahed | MD. Shaheduzzaman Shahed
100